## OpenProject Import
Phase | Type | Subject | Description | Priority | Estimated hours | Owner | Parent
Phase 2 | Feature | PostgreSQL Integration & Persistence | Production-ready database foundation and durable pipeline metadata. | Priority 1 | 16 | Backend
Phase 2 | Task | Set up PostgreSQL | Run PostgreSQL in docker-compose. | Priority 1 | 4 | Backend | PostgreSQL Integration & Persistence
Phase 2 | Task | Add SQLAlchemy 2.x | Add SQLAlchemy ORM and database session setup. | Priority 1 | 4 | Backend | PostgreSQL Integration & Persistence
Phase 2 | Task | Configure Alembic | Create Alembic migration scaffolding and initial migration workflow. | Priority 1 | 3 | Backend | PostgreSQL Integration & Persistence
Phase 2 | Task | Create Pipeline ORM model | Persist pipeline definitions. | Priority 1 | 3 | Backend | PostgreSQL Integration & Persistence
Phase 2 | Task | Create PipelineVersion ORM model | Persist immutable pipeline versions. | Priority 1 | 3 | Backend | PostgreSQL Integration & Persistence
Phase 2 | Task | Create PipelineRun ORM model | Persist execution lifecycle and run metadata. | Priority 1 | 3 | Backend | PostgreSQL Integration & Persistence
Phase 2 | Task | Create NodeRun ORM model | Persist per-node execution information. | Priority 1 | 2 | Backend | PostgreSQL Integration & Persistence
Phase 2 | Task | Create Connection ORM model | Persist connection metadata. | Priority 2 | 3 | Backend | PostgreSQL Integration & Persistence
Phase 2 | Task | Create Artifact ORM model | Persist artifact metadata. | Priority 2 | 3 | Backend | PostgreSQL Integration & Persistence
Phase 2 | Task | Add database integration tests | Test ORM models and persistence behavior. | Priority 1 | 4 | Backend | PostgreSQL Integration & Persistence
Phase 2 | Feature | Pipeline Persistence | Save and load pipeline definitions durably. | Priority 1 | 8 | Backend
Phase 2 | Task | Implement pipeline save | Persist PipelineDefinition data. | Priority 1 | 4 | Backend | Pipeline Persistence
Phase 2 | Task | Implement pipeline load | Load stored pipeline definitions for execution/editing. | Priority 1 | 4 | Backend | Pipeline Persistence
Phase 2 | Feature | Job Queue & Worker | Run long-running pipelines asynchronously without blocking the API. | Priority 1 | 20 | Backend
Phase 2 | Task | Define PipelineJob lifecycle | Define queued, running, succeeded, and failed job states. | Priority 1 | 3 | Backend | Job Queue & Worker
Phase 2 | Task | Implement job persistence | Persist jobs and their lifecycle state. | Priority 1 | 4 | Backend | Job Queue & Worker
Phase 2 | Task | Implement queue interface | Create an abstraction for submitting and claiming jobs. | Priority 1 | 3 | Backend | Job Queue & Worker
Phase 2 | Task | Implement worker process | Create an independent worker main loop. | Priority 1 | 5 | Backend | Job Queue & Worker
Phase 2 | Task | Implement worker job claiming | Safely claim queued jobs for execution. | Priority 1 | 3 | Backend | Job Queue & Worker
Phase 2 | Task | Add worker failure handling | Persist failures and make worker behavior resilient. | Priority 1 | 2 | Backend | Job Queue & Worker
Phase 2 | Task | Return job_id from API | API should submit work and return a job identifier instead of blocking. | Priority 1 | 2 | Backend | Job Queue & Worker
Phase 2 | Task | Add frontend job status polling | Frontend polls job status after submission. | Priority 1 | 3 | Frontend | Job Queue & Worker
Phase 2 | Feature | Pipeline Versioning | Support draft and published pipeline versions. | Priority 1 | 10 | Backend
Phase 2 | Task | Add PipelineVersion table | Persist immutable pipeline versions. | Priority 1 | 3 | Backend | Pipeline Versioning
Phase 2 | Task | Implement draft pipeline lifecycle | Allow pipelines to remain editable in draft state. | Priority 1 | 2 | Backend | Pipeline Versioning
Phase 2 | Task | Implement publish flow | Publish a draft to create an immutable version. | Priority 1 | 2 | Backend | Pipeline Versioning
Phase 2 | Task | Execute specific pipeline version | Allow runs to reference an exact version. | Priority 1 | 2 | Backend | Pipeline Versioning
Phase 2 | Task | Add frontend Publish button | Expose publishing in the frontend. | Priority 1 | 1 | Frontend | Pipeline Versioning
Phase 2 | Feature | API Versioning & Error Contract | Standardize API paths and structured errors. | Priority 1 | 10 | Backend
Phase 2 | Task | Prefix routes with /api/v1/ | Move API routes under the v1 namespace. | Priority 1 | 4 | Backend | API Versioning & Error Contract
Phase 2 | Task | Create structured exception handlers | Return consistent error response objects. | Priority 1 | 2 | Backend | API Versioning & Error Contract
Phase 2 | Task | Create error code enum | Define stable machine-readable error codes. | Priority 1 | 1 | Backend | API Versioning & Error Contract
Phase 2 | Task | Add request ID correlation | Include request IDs in errors and logs. | Priority 1 | 1 | Backend | API Versioning & Error Contract
Phase 2 | Task | Add API error response model | Implement the documented error envelope with code, message, details, and request_id. | Priority 1 | 2 | Backend | API Versioning & Error Contract
Phase 2 | Feature | Connection Management | Manage database/S3 connection metadata for pipeline connectors. | Priority 2 | 16 | Backend
Phase 2 | Task | Connection CRUD API | Create, read, update, and delete connection definitions. | Priority 2 | 4 | Backend | Connection Management
Phase 2 | Task | Protect connection credentials | Keep secrets out of pipeline definitions and API responses. | Priority 2 | 4 | Backend | Connection Management
Phase 2 | Task | Test connection endpoint | Validate configured connections before use. | Priority 2 | 3 | Backend | Connection Management
Phase 2 | Task | Update source connectors for connections | Allow sources to resolve connection references. | Priority 2 | 2 | Backend | Connection Management
Phase 2 | Task | Update sink connectors for connections | Allow sinks to resolve connection references. | Priority 2 | 2 | Backend | Connection Management
Phase 2 | Task | Connection management UI | Frontend for configuring and testing connections. | Priority 2 | 1 | Frontend | Connection Management
Phase 2 | Feature | Run History & Monitoring | Record execution status, timing, metrics, errors, and structured logs. | Priority 2 | 24 | Both
Phase 2 | Task | Persist PipelineRun and NodeRun | Record every execution and per-node results. | Priority 2 | 6 | Backend | Run History & Monitoring
Phase 2 | Task | Implement structured execution logging | Store structured JSON logs for runs. | Priority 2 | 4 | Backend | Run History & Monitoring
Phase 2 | Task | Run history API | Expose historical runs and execution metrics. | Priority 2 | 4 | Backend | Run History & Monitoring
Phase 2 | Task | Run details UI | Display run status, timing, node results, and errors. | Priority 2 | 6 | Frontend | Run History & Monitoring
Phase 2 | Task | Add rows read/written metrics | Record per-node execution metrics. | Priority 2 | 4 | Backend | Run History & Monitoring
Phase 2 | Feature | Schema System | Discover, infer, derive, and validate schemas through the DAG. | Priority 2 | 16 | Backend
Phase 2 | Task | Create Schema model | Represent column, data type, nullable, and metadata. | Priority 2 | 4 | Backend | Schema System
Phase 2 | Task | Add read_schema() to sources | Allow sources to discover input schemas. | Priority 2 | 4 | Backend | Schema System
Phase 2 | Task | Add schema derivation to transforms | Compute output schemas from transformation metadata/configuration. | Priority 2 | 4 | Backend | Schema System
Phase 2 | Task | Add schema validation to DAG validator | Validate column existence and compatible types. | Priority 2 | 2 | Backend | Schema System
Phase 2 | Task | Schema preview endpoint | Expose computed schema information through the API. | Priority 2 | 2 | Backend | Schema System
Phase 2 | Feature | Data Preview | Provide bounded preview execution with row and time limits. | Priority 2 | 12 | Both
Phase 2 | Task | Implement bounded preview execution | Execute a node with bounded output. | Priority 2 | 3 | Backend | Data Preview
Phase 2 | Task | Artifact storage | Store preview results as artifacts. | Priority 2 | 3 | Backend | Data Preview
Phase 2 | Task | Configurable row limit and timeout | Limit preview size and execution duration. | Priority 2 | 2 | Backend | Data Preview
Phase 2 | Task | Preview UI component | Display intermediate node data. | Priority 2 | 3 | Frontend | Data Preview
Phase 2 | Task | Preview cache management | Cache preview results with TTL. | Priority 2 | 1 | Backend | Data Preview
Phase 2 | Feature | Testing & Integration | Validate the production-ready single-user MVP. | Priority 1 | 24 | Both
Phase 2 | Task | Database integration tests | Validate persistence and migrations. | Priority 1 | 4 | Backend | Testing & Integration
Phase 2 | Task | Worker integration tests | Validate queued execution and worker behavior. | Priority 1 | 5 | Backend | Testing & Integration
Phase 2 | Task | API integration tests | Validate versioned endpoints and structured errors. | Priority 1 | 4 | Backend | Testing & Integration
Phase 2 | Task | End-to-end pipeline execution test | Exercise JSON pipeline submission through worker execution and result. | Priority 1 | 5 | Both | Testing & Integration
Phase 2 | Task | Reach 40+ integration tests | Meet the Phase 2 success metric. | Priority 1 | 6 | Both | Testing & Integration
Phase 3 | Feature | Scheduling | Cron schedules, overlap policies, timezone support, and manual triggers. | Later | 12 | Backend
Phase 3 | Task | Schedule model & CRUD | Persist and manage schedules. | Later | 3 | Backend | Scheduling
Phase 3 | Task | Scheduler service | Run scheduled pipeline jobs. | Later | 4 | Backend | Scheduling
Phase 3 | Task | Schedule UI | Calendar and cron-builder interface. | Later | 3 | Frontend | Scheduling
Phase 3 | Task | Manual trigger endpoint | Trigger scheduled pipelines on demand. | Later | 2 | Backend | Scheduling
Phase 3 | Feature | Workspaces & Authorization | Support multiple workspaces and per-resource authorization. | Later | 16 | Both
Phase 3 | Task | Workspace CRUD | Create and manage workspaces. | Later | 3 | Backend | Workspaces & Authorization
Phase 3 | Task | Workspace membership | Add and remove members from workspaces. | Later | 3 | Backend | Workspaces & Authorization
Phase 3 | Task | Role-based access | Support admin/editor/viewer roles. | Later | 4 | Backend | Workspaces & Authorization
Phase 3 | Task | Resource-level ACLs | Authorize access to workspace resources. | Later | 4 | Backend | Workspaces & Authorization
Phase 3 | Task | Workspace UI | Frontend workspace management. | Later | 2 | Frontend | Workspaces & Authorization
Phase 3 | Feature | Audit Logging | Track changes made to platform resources. | Later | 8 | Backend
Phase 3 | Feature | Advanced Data Quality Checks | Add advanced data quality validation. | Later | 12 | Backend
Phase 3 | Feature | Additional Sources | Add SQL and REST API source connectors. | Later | 12 | Backend
Phase 3 | Feature | Credentials Vault Integration | Integrate secure credential storage. | Later | 10 | Backend
Phase 3 | Feature | Artifact Retention Policies | Manage artifact lifecycle and retention. | Later | 6 | Backend

## Import Notes
Field | Purpose
Type | Uses OpenProject work package types Feature and Task. Ensure these types are enabled in the target project.
Subject | Work package title.
Description | Initial work package description.
Priority | Source roadmap priority; map to your project's actual OpenProject priority values if needed.
Estimated hours | Source roadmap estimate where specified; some subtask estimates are decomposed from the roadmap rather than explicitly stated in the source.
Owner | Backend, Frontend, or Both based on the source roadmap/dependency table.
Parent | Intended parent Feature for child Tasks.
Import method | OpenProject's Excel synchronization supports importing/updating work packages and parent-child hierarchy.
Important | OpenProject requires the corresponding work package types/fields to exist in the project before they can be synchronized.